## Traceability
backlog_id | phase | backlog | owner | deliverable | artifact | status | evidence
B1 | Phase 1 | Identify and fix the DB provider (MySQL or PostgreSQL) with a reason | Team | DB provider decision | docs/02_adr_log.xlsx (ADR-001), docs/07_schema_justification.md (Engine) | Done | CockroachDB v26.2 chosen; PG dialect; deviations recorded
B2 | Phase 1 | Read the requirement document and agree the module list | Team | Agreed module list | docs/01_er/module_map.md, docs/03_module_ownership.xlsx (Modules) | Done | 17 modules (11 docket + Tier 3 + 5 labelled extensions)
B3 | Phase 1 | Assign the common modules: Profile, and Jobs and Applications | Team | Common module assignment | docs/03_module_ownership.xlsx (Modules: Common) | Done | Profile and Jobs and Applications assigned to Team
B4 | Phase 1 | Identify entities for Profile | Team | Profile entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/profile.md | Done | profile: 90 tables (38 lookups)
B5 | Phase 1 | Validate the Profile entities | Team | Validated Profile entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/profile.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | profile: 90 tables (38 lookups)
B6 | Phase 1 | Identify entities for Jobs and Applications | Team | Jobs and Applications entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/jobs_applications.md | Done | jobs_applications: 99 tables (42 lookups)
B7 | Phase 1 | Validate the Jobs and Applications entities | Team | Validated Jobs and Applications entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/jobs_applications.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | jobs_applications: 99 tables (42 lookups)
B8 | Phase 1 | Identify relationships for Profile | Team | Profile relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/profile.md | Done | profile: 90 tables (38 lookups)
B9 | Phase 1 | Validate the Profile relationships | Team | Validated Profile relationships | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/profile.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | profile: 90 tables (38 lookups)
B10 | Phase 1 | Identify relationships for Jobs and Applications | Team | Jobs and Applications relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/jobs_applications.md | Done | jobs_applications: 99 tables (42 lookups)
B11 | Phase 1 | Validate the Jobs and Applications relationships | Team | Validated Jobs and Applications relationships | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/jobs_applications.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | jobs_applications: 99 tables (42 lookups)
B12 | Phase 1 | Identify columns for Profile | Team | Profile column list | 05_data_dictionary.xlsx (Columns); docs/01_er/profile.md | Done | profile: 90 tables (38 lookups)
B13 | Phase 1 | Validate the Profile columns | Team | Validated Profile columns | 05_data_dictionary.xlsx (Columns); docs/01_er/profile.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | profile: 90 tables (38 lookups)
B14 | Phase 1 | Identify columns for Jobs and Applications | Team | Jobs and Applications column list | 05_data_dictionary.xlsx (Columns); docs/01_er/jobs_applications.md | Done | jobs_applications: 99 tables (42 lookups)
B15 | Phase 1 | Validate the Jobs and Applications columns | Team | Validated Jobs and Applications columns | 05_data_dictionary.xlsx (Columns); docs/01_er/jobs_applications.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | jobs_applications: 99 tables (42 lookups)
B16 | Phase 1 | Combine entities and columns into the Profile design | Team | Profile design draft | 05_data_dictionary.xlsx (all sheets); docs/01_er/profile.md | Done | profile: 90 tables (38 lookups)
B17 | Phase 1 | Validate the Profile design | Team | Validated Profile design | 05_data_dictionary.xlsx (all sheets); docs/01_er/profile.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | profile: 90 tables (38 lookups)
B18 | Phase 1 | Combine entities and columns into the Jobs and Applications design | Team | Jobs and Applications design draft | 05_data_dictionary.xlsx (all sheets); docs/01_er/jobs_applications.md | Done | jobs_applications: 99 tables (42 lookups)
B19 | Phase 1 | Validate the Jobs and Applications design | Team | Validated Jobs and Applications design | 05_data_dictionary.xlsx (all sheets); docs/01_er/jobs_applications.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | jobs_applications: 99 tables (42 lookups)
B20 | Phase 1 | Add keys and constraints to Profile | Team | Profile keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/profile.md | Done | profile: 90 tables (38 lookups)
B21 | Phase 1 | Validate the Profile keys and constraints | Team | Validated Profile keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/profile.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | profile: 90 tables (38 lookups)
B22 | Phase 1 | Add keys and constraints to Jobs and Applications | Team | Jobs and Applications keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/jobs_applications.md | Done | jobs_applications: 99 tables (42 lookups)
B23 | Phase 1 | Validate the Jobs and Applications keys and constraints | Team | Signed Phase 1 design | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/jobs_applications.md; validated by docs/tools/lint_dictionary.py (0 errors) | Done | jobs_applications: 99 tables (42 lookups)
B24 | Phase 2 | Identify entities for Administration: users, roles, permissions and the audit trail | Member A | Administration entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/administration.md | Done | administration: 88 tables (42 lookups)
B25 | Phase 2 | Identify entities for Organisation and account: employer and client organisations, locations, and account administrators | Member B | Organisation entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/organisation_account.md | Done | organisation_account: 65 tables (27 lookups)
B26 | Phase 2 | Identify entities for Gig marketplace: gig requests, gig worker profiles, availability and gig applications | Member C | Gig entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/gig_marketplace.md | Done | gig_marketplace: 65 tables (31 lookups)
B27 | Phase 2 | Identify relationships for Administration, including user to role and role to permission | Member A | Administration relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/administration.md | Done | administration: 88 tables (42 lookups)
B28 | Phase 2 | Identify relationships for Organisation and account, including the organisation hierarchy and recruiter mapping | Member B | Organisation relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/organisation_account.md | Done | organisation_account: 65 tables (27 lookups)
B29 | Phase 2 | Identify relationships for Gig marketplace, including assignments, handoff references and ratings | Member C | Gig relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/gig_marketplace.md | Done | gig_marketplace: 65 tables (31 lookups)
B30 | Phase 2 | Identify columns for Administration, with data type, domain, nullability and sensitive data class | Member A | Administration column list | 05_data_dictionary.xlsx (Columns); docs/01_er/administration.md | Done | administration: 88 tables (42 lookups)
B31 | Phase 2 | Identify columns for Organisation and account, with data type, domain, nullability and sensitive data class | Member B | Organisation column list | 05_data_dictionary.xlsx (Columns); docs/01_er/organisation_account.md | Done | organisation_account: 65 tables (27 lookups)
B32 | Phase 2 | Identify columns for Gig marketplace, with data type, domain, nullability and sensitive data class | Member C | Gig column list | 05_data_dictionary.xlsx (Columns); docs/01_er/gig_marketplace.md | Done | gig_marketplace: 65 tables (31 lookups)
B33 | Phase 2 | Add keys and constraints for Administration, including role-based access enforcement and the append-only audit trail | Member A | Administration keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/administration.md; see mechanism rules in 06_business_rules.xlsx | Done | administration: 88 tables (42 lookups)
B34 | Phase 2 | Add keys and constraints for Organisation and account, including effective-dated recruiter mapping | Member B | Organisation keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/organisation_account.md | Done | organisation_account: 65 tables (27 lookups)
B35 | Phase 2 | Add keys and constraints for Gig marketplace, including the rule that gig windows cannot overlap for the same gig worker | Member C | Gig keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/gig_marketplace.md; see mechanism rules in 06_business_rules.xlsx | Done | gig_marketplace: 65 tables (31 lookups)
B36 | Phase 3 | Identify entities for Licences, seats, devices and sessions: licences, seats, devices, sessions, login attempts and revocation events | Member A | Licences entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/licences_devices.md | Done | licences_devices: 34 tables (15 lookups)
B37 | Phase 3 | Identify entities for Sourcing and consultant requests: sourcing requests, consultant openness, acceptance or decline decisions, outreach batches and recipients | Member B | Sourcing entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/sourcing_consultant.md | Done | sourcing_consultant: 42 tables (15 lookups)
B38 | Phase 3 | Identify entities for Subscriptions, wallet, payments and download history: plans, subscription periods, payment orders, wallet ledger, refunds, invoices and profile download events | Member C | Subscriptions entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/subscriptions_payments.md | Done | subscriptions_payments: 74 tables (35 lookups)
B39 | Phase 3 | Identify relationships for Licences, seats, devices and sessions, including licence to user, user to device, and session to device | Member A | Licences relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/licences_devices.md | Done | licences_devices: 34 tables (15 lookups)
B40 | Phase 3 | Identify relationships for Sourcing and consultant requests, including request to requirement, request to consultant, and recipient to candidate | Member B | Sourcing relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/sourcing_consultant.md | Done | sourcing_consultant: 42 tables (15 lookups)
B41 | Phase 3 | Identify relationships for Subscriptions, wallet, payments and download history, including subscription to licence, payment to subscription, and ledger entry to wallet | Member C | Subscriptions relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/subscriptions_payments.md | Done | subscriptions_payments: 74 tables (35 lookups)
B42 | Phase 3 | Identify columns for Licences, seats, devices and sessions, with data type, domain, nullability and sensitive data class | Member A | Licences column list | 05_data_dictionary.xlsx (Columns); docs/01_er/licences_devices.md | Done | licences_devices: 34 tables (15 lookups)
B43 | Phase 3 | Identify columns for Sourcing and consultant requests, with data type, domain, nullability and sensitive data class | Member B | Sourcing column list | 05_data_dictionary.xlsx (Columns); docs/01_er/sourcing_consultant.md | Done | sourcing_consultant: 42 tables (15 lookups)
B44 | Phase 3 | Identify columns for Subscriptions, wallet, payments and download history, with data type, domain, nullability and sensitive data class | Member C | Subscriptions column list | 05_data_dictionary.xlsx (Columns); docs/01_er/subscriptions_payments.md | Done | subscriptions_payments: 74 tables (35 lookups)
B45 | Phase 3 | Add keys and constraints for Licences, seats, devices and sessions, including the mechanism that enforces the device limit under concurrent logins | Member A | Licences keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/licences_devices.md; see mechanism rules in 06_business_rules.xlsx | Done | licences_devices: 34 tables (15 lookups)
B46 | Phase 3 | Add keys and constraints for Sourcing and consultant requests, including the rule that a consultant can act only on a requirement open to consultants | Member B | Sourcing keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/sourcing_consultant.md; see mechanism rules in 06_business_rules.xlsx | Done | sourcing_consultant: 42 tables (15 lookups)
B47 | Phase 3 | Add keys and constraints for Subscriptions, wallet, payments and download history, including non-overlapping subscription periods and the append-only ledger rule | Member C | Subscriptions keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/subscriptions_payments.md; see mechanism rules in 06_business_rules.xlsx | Done | subscriptions_payments: 74 tables (35 lookups)
B48 | Phase 4 | Identify entities for Notifications, preferences and community: notification preferences, job alert preferences, language preference, privacy settings, notification deliveries, community posts, reactions, support tickets, FAQs and referral events | Team | Notifications entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/notifications_community.md | Done | notifications_community: 93 tables (28 lookups)
B49 | Phase 4 | Identify entities for Analytics layer and reporting marts: dimensions, facts and aggregates for the KPIs in Section 8 | Team | Analytics entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/analytics.md | Done | analytics: 80 tables (5 lookups)
B50 | Phase 4 | Identify entities for the shared team items: credentials, consent records, identity sessions, the audit trail and blocking lists for candidates, employers, recruiters and consultants | Team | Shared team entity list | 05_data_dictionary.xlsx (Tables); docs/01_er/administration.md | Done | administration: 88 tables (42 lookups)
B51 | Phase 4 | Identify relationships for Notifications, preferences and community, including preference to user, delivery to notification, and post to reaction | Team | Notifications relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/notifications_community.md | Done | notifications_community: 93 tables (28 lookups)
B52 | Phase 4 | Identify relationships for Analytics layer and reporting marts, including fact to dimension and aggregate to fact | Team | Analytics relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/analytics.md | Done | analytics: 80 tables (5 lookups)
B53 | Phase 4 | Identify relationships for the shared team items, including credential to user, consent to user, session to user, audit event to actor, and blocking entry to blocker and blocked party | Team | Shared team relationship model | 05_data_dictionary.xlsx (ForeignKeys), docs/03_module_ownership.xlsx (CrossModuleFK); docs/01_er/administration.md | Done | administration: 88 tables (42 lookups)
B54 | Phase 4 | Identify columns for Notifications, preferences and community, with data type, domain, nullability and sensitive data class | Team | Notifications column list | 05_data_dictionary.xlsx (Columns); docs/01_er/notifications_community.md | Done | notifications_community: 93 tables (28 lookups)
B55 | Phase 4 | Identify columns for Analytics layer and reporting marts, with data type, domain, nullability and sensitive data class | Team | Analytics column list | 05_data_dictionary.xlsx (Columns); docs/01_er/analytics.md | Done | analytics: 80 tables (5 lookups)
B56 | Phase 4 | Identify columns for the shared team items, with data type, domain, nullability and sensitive data class, including the sensitive class for credentials | Team | Shared team column list | 05_data_dictionary.xlsx (Columns); docs/01_er/administration.md | Done | administration: 88 tables (42 lookups)
B57 | Phase 4 | Add keys and constraints for Notifications, preferences and community, including the high-volume write path for deliveries | Team | Notifications keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/notifications_community.md; see mechanism rules in 06_business_rules.xlsx | Done | notifications_community: 93 tables (28 lookups)
B58 | Phase 4 | Add keys and constraints for Analytics layer and reporting marts, including slowly changing dimension keys and aggregate refresh rules | Team | Analytics keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/analytics.md; see mechanism rules in 06_business_rules.xlsx | Done | analytics: 80 tables (5 lookups)
B59 | Phase 4 | Add keys and constraints for the shared team items, including the append-only audit trail, the unique constraint on credentials, and the rule that a blocked party cannot see the blocker's candidate | Team | Shared team keys and constraints | 05_data_dictionary.xlsx (Constraints, Indexes), docs/06_business_rules.xlsx; docs/01_er/administration.md; see mechanism rules in 06_business_rules.xlsx | Done | administration: 88 tables (42 lookups)
B60 | Phase 5 | Seed Master data and Profile at laptop scale: 1 million candidate profiles with duplicates and multilingual names, and all reference lookups populated | Team | Seeded Master data and Profile | docs/12_seed_and_validation_plan.md (Seed design, load order) | Design done; execution pending
B61 | Phase 5 | Seed Jobs and Applications at laptop scale: 100,000 job requirements and 5 million applications across the full status pipeline | Team | Seeded Jobs and Applications | docs/12_seed_and_validation_plan.md | Design done; execution pending
B62 | Phase 5 | Seed Administration, Organisation and account, and Gig marketplace: users, roles, organisations, mapped recruiters, gig requests and assignments including overlap attempts | Member A | Seeded Administration, Organisation and Gig data | docs/12_seed_and_validation_plan.md (incl. gig/overlap negative tests) | Design done; execution pending
B63 | Phase 5 | Seed Licences, Sourcing and Subscriptions: licences, sessions, sourcing requests, subscriptions, payments, refunds and downloads | Member B | Seeded Licences, Sourcing and Subscriptions data | docs/12_seed_and_validation_plan.md (licence, sourcing, subscription, refund, download) | Design done; execution pending
B64 | Phase 5 | Seed Notifications, Analytics and the shared team items: notification deliveries, community posts, credentials, consent records, audit events and blocking entries | Member C | Seeded Notifications, Analytics and shared team data | docs/12_seed_and_validation_plan.md | Design done; execution pending
B65 | Phase 5 | Write and run the fixed query set (about twelve queries) covering functional, transactional, lookup and performance cases, with execution plans for the top ten | Team | Query set with output and execution plans | docs/11_performance_indexing_plan.md (fixed query set, top-10 EXPLAIN) | Design done; execution pending
B66 | Phase 5 | Validate the seeded data against the data standards in Section 5 and the coverage gap register, and record any failures | Team | Seed validation report | docs/12_seed_and_validation_plan.md (Section 5 validation SQL), docs/10_competitor_benchmark.xlsx (Gap register) | Design done; execution pending
B67 | Phase 5 | Write module-specific queries and validate the seeded data for each module, and record the results | Member A | Module query results for Administration, Organisation and Gig | docs/12_seed_and_validation_plan.md (module queries) | Design done; execution pending
B68 | Phase 5 | Write module-specific queries and validate the seeded data for each module, and record the results | Member B | Module query results for Licences, Sourcing and Subscriptions | docs/12_seed_and_validation_plan.md (module queries) | Design done; execution pending
B69 | Phase 5 | Write module-specific queries and validate the seeded data for each module, and record the results | Member C | Module query results for Notifications, Analytics and shared items | docs/12_seed_and_validation_plan.md (module queries) | Design done; execution pending
B70 | Phase 5 | Measure baseline query latency for the top ten queries using the method in Section 10 (hardware, dataset size, query text, number of runs, p50, p95, p99) | Team | Performance baseline report | docs/11_performance_indexing_plan.md (measurement method) | Design done; execution pending
B71 | Phase 5 | Identify and justify one index per module with a before-and-after measurement | Member A | Index justification for Administration, Organisation and Gig | docs/11_performance_indexing_plan.md, docs/11_index_catalogue.xlsx | Design done; execution pending
B72 | Phase 5 | Identify and justify one index per module with a before-and-after measurement | Member B | Index justification for Licences, Sourcing and Subscriptions | docs/11_performance_indexing_plan.md, docs/11_index_catalogue.xlsx | Design done; execution pending
B73 | Phase 5 | Identify and justify one index per module with a before-and-after measurement, and the partitioning strategy for the application and notification tables | Member C | Index justification for Notifications, Analytics and partitioning | docs/11_performance_indexing_plan.md (partitioning for application and notification tables) | Design done; execution pending
B74 | Phase 5 | Write the full-scale extrapolation to 10 million profiles and 100 million applications, identifying the query expected to degrade first and why | Team | Extrapolation to full scale | docs/11_performance_indexing_plan.md (extrapolation + first query to degrade) | Design done; measurement pending
B75 | Phase 5 | Define PII handling for each module: encryption, tokenisation or masking for contact details, national identifiers and tax identifiers, with the approach stated | Member A | PII handling notes for Administration, Organisation and Gig | docs/15_security_design_note.md (PII: Administration, Organisation, Gig) | Done
B76 | Phase 5 | Define PII handling for each module: encryption, tokenisation or masking for payment references and credentials, with the approach stated | Member B | PII handling notes for Licences, Sourcing and Subscriptions | docs/15_security_design_note.md (PII: Licences, Sourcing, Subscriptions) | Done
B77 | Phase 5 | Define PII handling for each module: encryption, tokenisation or masking for candidate contact details in notifications and community, with the approach stated | Member C | PII handling notes for Notifications, Analytics and shared items | docs/15_security_design_note.md (PII: Notifications, Analytics, shared) | Done
B78 | Phase 5 | Write the threat model for the schema and the controls applied: access control by role, audit trail, password hashing, and session controls | Team | Threat model and controls | docs/14_threat_model.md | Done
B79 | Phase 5 | Test that access rules hold for each module: a user cannot read or change data outside their role, and the audit trail records every sensitive action | Team | Access and audit test results | docs/13_rbac_matrix.xlsx, docs/14_threat_model.md (test cases), docs/12_seed_and_validation_plan.md | Design done; test execution pending
B80 | Phase 5 | Perform a backup and restore of the seeded database, and record the time taken against the RTO in Section 10 | Team | Backup and restore log | docs/20_backup_restore_log.xlsx (template and procedure) | Template done; measurement pending
B81 | Phase 5 | Write the security design note, combining the module notes, the threat model and the audit design | Team | Security design note | docs/15_security_design_note.md | Done
B82 | Phase 5 | Gate 2 review: confirm the seeded database, query set, performance evidence, backup restore and security note are complete | Team | Gate 2 sign-off | docs/00_milestone_traceability.xlsx (this file), docs/README.md | Documentation gate done; execution gate pending

## Modules
module_key | module | owner | tables | lookup_tables
administration | Administration | Member A | 88 | 42
analytics | Analytics layer and reporting marts | Team | 80 | 5
ext_ads | Extension: Ads and sponsored placements | Team | 79 | 36
ext_learning | Extension: Learning and assessments marketplace | Team | 112 | 43
ext_matching | Extension: Recommendations and matching signals | Team | 78 | 32
ext_network | Extension: Network, connections and graph | Team | 88 | 36
ext_talent_ops | Extension: Talent operations (onboarding, background checks, CRM, trust and safety) | Team | 125 | 61
gig_marketplace | Gig marketplace | Member C | 65 | 31
jobs_applications | Jobs and Applications | Team | 99 | 42
licences_devices | Licences, seats, devices and sessions | Member A | 34 | 15
master_data | Master data | Team | 70 | 42
notifications_community | Notifications, preferences and community | Team | 93 | 28
organisation_account | Organisation and account | Member B | 65 | 27
profile | Profile | Team | 90 | 38
sourcing_consultant | Sourcing and consultant requests | Member B | 42 | 15
subscriptions_payments | Subscriptions, wallet, payments and download history | Member C | 74 | 35
tier3_reference | Tier 3 reference domains (optional) | Team | 24 | 10

## Section4Coverage
tier | domain | module | key_tables (verify in dictionary)
Tier 1 | Identity and accounts | administration | app_user, user_credential, app_role, identity_session, user_consent
Tier 1 | Candidate profile core | profile | candidate_profile, candidate_education, candidate_experience, candidate_skill
Tier 1 | Employer and client organisation | organisation_account | organisation, organisation_location, recruiter_organisation_mapping
Tier 1 | Job requirement lifecycle | jobs_applications | job_requirement, job_position
Tier 1 | Applications and pipeline | jobs_applications | job_application, job_application_status_history
Tier 1 | Sourcing and consultant requests | sourcing_consultant | sourcing_request, outreach_batch, outreach_recipient
Tier 1 | Wallet and credits | subscriptions_payments | wallet, wallet_ledger_entry
Tier 1 | Audit and error logging | administration | audit_event, error_log
Tier 1 | Master data | master_data | country, city, skill, qualification, industry, job_role
Tier 1 | Notifications and alert preferences | notifications_community | notification, notification_delivery, job_alert_preference
Tier 1 | Gig marketplace | gig_marketplace | gig_request, gig_worker_profile, gig_application, gig_assignment, gig_slot
Tier 1 | Licences and seats | licences_devices | licence, licence_seat
Tier 1 | Devices and sessions | licences_devices | device, device_session, device_slot, login_attempt
Tier 1 | Subscriptions and plans | subscriptions_payments | subscription_plan, subscription, subscription_period
Tier 1 | Payments and transaction history | subscriptions_payments | payment_order, invoice, refund
Tier 1 | Account and organisation | organisation_account | account, account_admin, organisation_hierarchy
Tier 1 | Preferences | notifications_community | notification_preference, language_preference, privacy_setting
Tier 1 | Profile projects | profile / gig_marketplace | candidate_project, gig_worker_project
Tier 1 | Profile download history | subscriptions_payments | profile_download
Tier 2 | Resume versions and templates | profile | resume, resume_template
Tier 2 | Community posts and reactions | notifications_community | community_post, community_reaction
Tier 2 | Profile view history | profile | candidate_profile_view
Tier 3 | Salary benchmarks, company ratings, trending, dashboards, feature flags | tier3_reference | optional module
Extension | Network, matching, ads, learning, talent operations | ext_* | product-suite scope increase; see ADR log